Smart CCTV Analytics Platform

Project Charter

Prepared by: [Your Name]

Course: [Capstone Course Name / Section]

Instructor: [Instructor Name]

Date: September 13, 2026

# Table of Contents

(Right-click and “Update Field” in Word to populate page numbers.)

# 1  Project Background (10%)

## 1.1  Problem/Opportunity Description

Security operators today rely on continuous human monitoring or after-the-fact manual review of camera footage to identify incidents — a process that is slow, labor-intensive, and error-prone. Small businesses, campuses, and residential complexes often cannot afford dedicated 24/7 monitoring staff, so most footage is only reviewed reactively, after an incident is already known to have occurred. This creates an opportunity to apply computer vision and backend engineering to automatically detect, log, and index security-relevant events — turning hours of raw video into a searchable, actionable record without requiring full-time human monitoring.

## 1.2  Benefits

- Reduces the time required to locate a specific incident from hours of manual review to a targeted search.

- Enables proactive alerting for after-hours or restricted-zone activity instead of purely reactive review.

- Provides an auditable historical record of camera activity for incident investigation and accountability.

- Demonstrates an architecture (detection service + backend API + dashboard) that scales beyond the prototype's camera count.

- Gives the student direct, resume-relevant experience integrating a computer vision pipeline with a secured, production-style backend and frontend.

## 1.3  Goals

- Deliver a working, cloud-hosted prototype that detects and tracks people and vehicles in video footage and logs them as searchable events.

- Meet all capstone course requirements: GitHub-based version control, weekly progress reporting, full SDLC documentation, and a security-hardened, cloud-deployed final product.

- Produce a system architecture and codebase that could realistically be extended toward a real deployment beyond the course.

## 1.4  Stakeholders and Clients

The table below summarizes the primary parties with an interest in this project and their level of influence over its direction.

| Stakeholder | Role & Interest | Influence |
| --- | --- | --- |
| Student (Project Owner) | Designs, builds, and delivers the platform solo; directly responsible for the outcome. | High |
| Course Instructor / TA (Project Sponsor) | Approves scope, evaluates milestones, and defines the grading criteria for success. | High |
| Security Operator (hypothetical end user) | Would use the dashboard daily to search and review flagged events; usability and accuracy directly affect them. | Medium |
| Site / Business Owner (hypothetical end user) | Would rely on the system to reduce manual security review workload and cost. | Low |
| University / Program (indirect) | Provides course infrastructure and context; no direct involvement in build decisions. | Low |

# 2  Project Scope (10%)

## 2.1  Objectives

- Achieve at least 80% detection precision for person/vehicle classes on a held-out test set of sample footage by Week 12.

- Deploy a fully functional, publicly accessible instance of the application to a cloud platform (AWS or GCP) by Week 13.

- Implement role-based access control and encrypted storage for all video/event data by Week 11.

- Support search and filtering of the event history by camera, time range, and event type by Week 10.

- Submit weekly progress reports and maintain an active GitHub repository and Jira/Trello board throughout the semester.

## 2.2  Deliverables

- Working, cloud-hosted web application (detection + tracking pipeline, backend API, frontend dashboard).

- Source code repository on GitHub with commit history reflecting incremental development.

- Full SDLC documentation set: requirements/analysis document, system design document (architecture + ER diagrams), and test plan with results.

- Weekly status reports submitted to the instructor/TA.

- Final written project report.

- Final presentation and live demo.

## 2.3  Out of Scope

- Integration with live, physical IP camera hardware — the prototype uses recorded or sample footage.

- Facial recognition or identification of specific individuals — excluded for privacy/ethical reasons and to avoid biometric-data regulatory exposure.

- A native mobile application — web dashboard only, given the semester timeline.

- Multi-tenant support for multiple unrelated organizations — single-deployment scope only.

- Integration with third-party alarm or law-enforcement dispatch systems.

# 3  Project Plan (30%)

## 3.1  Approach and Methodology

As a solo project, development follows a personal Agile approach structured around weekly sprints, using a Trello or Jira board to track tasks and a GitHub repository (feature branches, self-reviewed pull requests) for version control and change history. Each week begins with a short planning check-in against the backlog and ends with a submitted progress report. A working, demonstrable increment of the system will be maintained from Week 7 onward so the project never regresses to a fully broken state. In place of peer code review, a personal pre-merge checklist (automated tests passing, linting clean, self-review of the diff) is applied before merging, and unit tests are added incrementally rather than saved for a single testing phase at the end.

## 3.2  Project Timeline

Phase-level summary:

| Phase | Weeks | Key Activities | Deliverable |
| --- | --- | --- | --- |
| 1. Initiation & Design | 1–3 | Requirements gathering, architecture & ER diagram, cloud/environment setup | Design doc; “Hello World” deployed to cloud |
| 2. Core Pipeline Development | 4–7 | Detection model integration, tracking, backend core (API, DB, auth), pipeline integration | End-to-end detect → log pipeline |
| 3. Midpoint Review | 8 | Internal demo, instructor checkpoint, catch-up buffer | Progress demo + report |
| 4. Frontend & Search | 9–10 | Dashboard build, search/filter features, clip playback | Functional UI |
| 5. Security & Testing | 11–12 | RBAC enforcement, encryption, audit logging, unit/integration testing | Security checklist complete; test report |
| 6. Deployment & Documentation | 13–14 | Cloud deployment, final report compilation | Live hosted URL; draft final report |
| 7. Final Delivery | 15 | Polish, rehearsal, submission | Final report + presentation |

Detailed weekly breakdown:

| Wk | Focus | Key Deliverables |
| --- | --- | --- |
| 1 | Kickoff — roles, GitHub repo, Jira/Trello board, requirements gathering | Analysis doc (draft); Weekly Report #1 |
| 2 | System design — use case diagrams, ER diagram, API contract, finalize architecture | Design doc v1 |
| 3 | Environment setup — cloud account, repo scaffolding (Spring Boot + React), CI skeleton | “Hello world” deployed to cloud |
| 4 | Detection pipeline — dataset prep, integrate YOLOv8, baseline test | Working detection on sample footage |
| 5 | Tracking + event logic — ByteTrack/DeepSORT, define event rules | Tracked objects → structured events |
| 6 | Backend core — camera management API, event schema, JWT auth, RBAC skeleton | Core API endpoints functional |
| 7 | Integration — connect detection service to backend, encrypted clip storage | End-to-end pipeline working |
| 8 | Midpoint demo, catch-up buffer | Progress report; working E2E demo |
| 9 | Frontend build — dashboard shell, camera list, recent events feed | Basic UI functional |
| 10 | Search & filtering — query API, pagination, clip playback | Full search/filter UX |
| 11 | Security hardening — audit logging, RBAC testing, HTTPS, secrets management | Security checklist complete |
| 12 | Testing — unit tests, model evaluation metrics, integration testing, bug fixes | Test report + model metrics |
| 13 | Cloud deployment — containerize, deploy full stack, smoke test | Live hosted URL |
| 14 | Documentation — compile SDLC artifacts into final report, user guide | Final report draft |
| 15 | Polish, rehearse, submit | Final report + presentation |

## 3.3  Success Criteria

- All Section 2.1 objectives met by their stated deadlines.

- Detection pipeline achieves ≥80% precision on the held-out test set.

- Application deployed and reachable via a public URL, with uptime maintained through the final demo.

- Security checklist (Section 3.5) fully implemented and demonstrable in a live walkthrough.

- All required SDLC artifacts submitted and weekly reports filed with no missed weeks.

- Positive instructor/TA feedback at the Week 8 midpoint checkpoint with no major scope concerns raised.

## 3.4  Issues and Policy Implications

- Privacy and surveillance ethics: the system detects people in video even as a prototype. Only public/sample datasets or footage of consenting individuals will be used for development and demos — no unconsented recording of real bystanders.

- Data retention: event logs and clips are retained only for the duration of the course project and deleted after final grading, since this is not a live production deployment.

- Regulatory awareness: a real-world deployment of this kind of system would need to account for state/local surveillance and biometric privacy laws (e.g., notice requirements, or statutes like Illinois' BIPA if biometric identification were ever added). This is noted as a design constraint even though facial recognition is explicitly out of scope.

- Personal availability: as a solo project running alongside other coursework, weekly capacity may vary; sprint planning builds in buffer time rather than assuming a fixed number of hours every week.

## 3.5  Risk Management Plan

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Detection model accuracy too low for demo | Medium | High | Use a proven pretrained YOLOv8 model rather than training from scratch; validate accuracy early (Wk 4–5) while there's time to adjust. |
| Cloud hosting costs exceed budget | Low–Med | Medium | Use free-tier/student credits; keep inference on-demand rather than an always-on GPU instance; monitor spend weekly. |
| Integration delays between detection service and backend | Medium | High | Define the API contract in Wk 2 before either side is built; integrate early (Wk 7), not at the end. |
| Sole developer unavailability (illness, exam load, burnout) | Medium | High | Buffer time built into the schedule (Wk 8 checkpoint); keep documentation and commit history current so lost time can be recovered quickly; prioritize core features first so a minimum viable version always exists. |
| All technical responsibility on one person (no teammate to share load or unblock issues) | High | High | Scope is calibrated to what one developer can realistically build in 15 weeks (see Section 2.3); lean on pretrained models and managed cloud services rather than building components from scratch; use instructor/TA office hours proactively when blocked. |
| Scope creep beyond the 15-week timeline | Medium | Medium | Objectives and out-of-scope list fixed upfront (Section 2); new requests deferred to a future-work list. |
| Security vulnerabilities in the deployed app | Low–Med | High | Dedicated security-hardening week (Wk 11) plus continuous dependency scanning (Dependabot). |

## 3.6  Service Transition

Since this is an academic capstone rather than a commercial rollout, “transition” here means a clean handover of a working system and its documentation, rather than a live operational cutover. At project close, the student will:

- Provide a README and setup guide sufficient for the instructor/TA (or a future student continuing the project) to run the system locally and understand the cloud deployment.

- Document all environment variables, the secrets-management approach, and infrastructure configuration so the deployment is reproducible without depending on the developer's personal machine setup.

- Tag a final release version in GitHub corresponding to the submitted deliverable.

- Note in the final report which components would need rework before a genuine production deployment (e.g., replacing sample footage with live camera ingestion).

## 3.7  Options Analysis

| Decision Area | Options Considered | Chosen Option | Rationale |
| --- | --- | --- | --- |
| Detection approach | (A) Train a custom model from scratch (B) Fine-tune a pretrained model (C) Third-party vision API (e.g., AWS Rekognition) | (B) Pretrained YOLOv8 | Reliable accuracy without a multi-week labeling effort; self-hosted inference keeps costs predictable and demonstrates real ML integration, unlike a pure API call. |
| Cloud provider | (A) AWS (B) GCP (C) Azure | (A) AWS | Broad documentation, student credit availability, and personal familiarity from prior coursework. |
| Database | (A) PostgreSQL (B) MongoDB | (A) PostgreSQL | Camera/event/user data is naturally relational, and search/filter requirements map cleanly onto SQL queries. |
| Object tracking | (A) ByteTrack (B) DeepSORT (C) No tracking (per-frame only) | (A) ByteTrack (DeepSORT fallback) | Prevents duplicate event logging across frames; lighter-weight than DeepSORT while accurate enough for prototype needs. |

# 4  Technical Features (10%)

| Feature | Description |
| --- | --- |
| Object detection & tracking | Detects people and vehicles per frame (YOLOv8) and tracks them across frames (ByteTrack) so each real-world object is logged once, not per-frame. |
| Event rule engine | Converts raw tracked detections into meaningful events: loitering beyond a time threshold, restricted-zone entry, after-hours vehicle activity. |
| Searchable event history | REST API and UI supporting filtering by camera, time range, and event type, with linked clip/thumbnail playback. |
| Camera management | Admin interface to register and manage camera sources and assign per-camera access permissions. |
| Authentication & RBAC | JWT-based authentication with operator vs. admin roles enforced at the API layer, not just hidden in the UI. |
| Encrypted, audited storage | Video clips and thumbnails encrypted at rest; every view/search recorded in an audit log. |
| Cloud-native deployment | Containerized services (Docker) deployed to AWS/GCP with CI/CD via GitHub Actions. |

# 5  Project Organization and Staffing (20%)

As a solo project, the student reports directly to the course instructor/TA, who acts as project sponsor and approves scope and milestone completion. All role areas below are held by the same person; splitting them here is a planning and time-allocation tool for balancing effort across the project's technical areas, not a division of labor across people.

| Role Area | Time Allocation | Responsibilities |
| --- | --- | --- |
| Backend Engineering | ~35% | Sprint planning; Spring Boot API; database schema and access control; deployment coordination. |
| ML / Computer Vision | ~35% | Detection and tracking pipeline; model selection and evaluation; event-rule logic. |
| Frontend Engineering | ~20% | React dashboard; search/filter UX; integration testing. |
| Documentation & Reporting | ~10% | Weekly reports, SDLC artifacts, final report and presentation. |

This allocation is a planning guideline, not a fixed weekly split — actual time shifts by phase (e.g., ML-heavy in Weeks 4–5, frontend-heavy in Weeks 9–10, as shown in the Section 3.2 timeline).

## Communication Plan

- Weekly self-review check-in against the sprint board to assess progress and re-prioritize the coming week.

- Written weekly status report submitted to the instructor/TA every week without exception.

- Sprint board (Jira/Trello) updated continuously and reviewed at each weekly check-in.

- Instructor/TA office hours used proactively when blocked, since there is no teammate to unblock with directly.

# 6  Project Budget (20%)

As an academic prototype, actual cash outlay is expected to be minimal and largely covered by cloud student credits. A labor-cost estimate is included below as well, purely as a budgeting exercise — no payment actually occurs, since this is coursework rather than a commercial engagement.

| Category | Item | Est. Cost | Notes |
| --- | --- | --- | --- |
| Cloud Infrastructure | Compute (on-demand inference, EC2/Cloud Run) | $0–$50 | Covered by AWS Educate / GCP student credits where available; on-demand (not always-on GPU) keeps this low. |
| Cloud Infrastructure | Storage (S3/GCS for clips & thumbnails, encrypted) | $0–$20 | Small footage volume expected for a prototype-scale demo. |
| Cloud Infrastructure | Data transfer | $0–$10 | Minimal at demo-scale traffic. |
| Software & Tools | GitHub, Jira/Trello, GitHub Actions (CI/CD) | $0 | Free tiers sufficient for a solo developer's project scope. |
| Software & Tools | Pretrained models & open-source libraries (YOLOv8, ByteTrack, etc.) | $0 | Open-source / permissively licensed. |
| Labor (illustrative only) | 1 developer × ~18 hrs/wk × 15 wks ≈ 270 person-hours at an illustrative $40/hr junior-dev rate | ≈ $10,800 | Demonstrates budgeting methodology only — no actual payment occurs. |
| Contingency | 15% of infrastructure cost estimate | ≈ $12 | Buffer for unexpected usage spikes. |

Total cash outlay (infrastructure + tools): approximately $0–$90 for the semester, expected to be fully covered by free tiers and student credits.

Total illustrative budget (including labor): approximately $10,800 — included only to demonstrate standard project budgeting methodology, as required by this charter template.